## Sheet1
Customers
| BRX mod TDS ringing | done
Lumen | gam-12 winbond to franklin | done
Lumen | deliver latest 1.4.0 to lumen | done
Parity | virtuoso for vistana | done
| Poll DSLAM lumen | done
Lumen | Debug PON SFP drop packets | done
| Meraki switch and AP | done
| new design G1001-MR defect Telus | done
| swap GAM cold start WoW | done
Lumen | BRX-XLR Calix old C7 blade | done
| 1.0.2 VIEW | done
| investigate bad G1001-MR rivervalley | done
| VIEW golden config | done
| VIEW firmware HomeGrid no password | done
| LCMP with password | done
| install script Steve | done
Lumen | Lumen speedtest issue 1.2 vs 1.4 | done
Lumen | Lumen 20:80 | done
| quote Hilton phoenix | done
| quote rancho inn San Diego | Done |  |  | JC
| quote Long beach leisure world | Done |  |  | JC
Lumen | LBE 26 AWG | done
Lumen | Champion one 2.5 vs 1G | done |  |  | luc
Lumen | Lumen short loop | done |  |  | luc
View | libcurl | done
Lumen | deliver latest 1.4.0 | done
Lumen | frame too long | done |  |  | ??? Stev mention it. Nobody else, consider non issue
Lumen | vectorboost SISO bad | done |  |  | remove automatic notch
Sail | SFP stopped working | done |  |  | customer sais ok !!
Lumen | new piggyback MIMO PCN lumen | don't do it |  |  | pierre said old pcn covers both
Lumen | SISO performance issue |  |  |  | maybe sr3
Novus | igmp queries Cisco 4500x |  | JF |  | firmware change ACL, done in 1.5.4, need to return 4500
Novus | snmp change 1.2 to 1.4, mac retreive | done
Nuvision | bad speedtest | don't do it |  |  | jk
| RMA flex | done
Caesars | G1002-C ETH LED on | done |  |  | not reproducible, trial over.
| Tucowinc 2-tags coax | done
| View DNS malformed packet | done
| Telus new MR SR2 | done
Caesars | password Philip | done
Lumen | Cynthia punch tool and RMA inductance | done |  |  | I did and pierre did explain
Lumen | 2 GAM same binder |  |  |  | 2 driver 1 engine, fail, sr1 pre-test not good, maybe sr3
Aruba | G1002-C+ freeze at boot | done |  |  | ron, issue ground, fix with wire between rail
Lumen | list of traps | don't do it |  |  | Brian is gone
Lumen | virtuoso 2.0 | done
Lumen | option-82 comply to tr-101 | in progress | Eric | 1.5.5
Ting Internet | snmp trap when quarantine endpoint newly discovered |  |  |  | minor feature enhancement
Marriott | changelog 1.5 | done
Ting internet | 950/250 on coax | done |  |  | wait maxlinear…. 7.12
Ting Internet | counters | done
Ting Internet | DHCP user configurable option-82 | in progress | Eric | 1.5.5
Ting Internet | and IPv6 insertion option 18/37 |  | Eric | 1.5.6
Co-Mo | 3 vlans remap ? |  |  | 1.5.6 | spring 2023
Patriot | sonar ? | don't do it |  |  | jk… en theorie pas mon probleme
CIK tel | mac limit on the endpoint. Dhcp limit instead not acceptable |  |  |  | 2023-01-01
Consolidated | performance issue | done |  |  | short loop need upgrade to auto notch
Parity | datasheet G1002/G2002 and PWR injector | done
nonius | phillips tv cable | done
Oak Leaf | G1001-MP dead, no LED | done |  |  | damaged, 3 more to come
DZS | snmp alarm and JSON stats | done
Accessparks | HPF diplexer | done |  |  | 3, 8$ 20 projects x 30
Smartera | issue daisy-chain | done
Parity/Vistana | all gam 100% cpu. 90% multicast/broadcast | done |  |  | old ruckus multicast
Consolidated | US issue, Harry | done |  |  | CRX ok. MRX not good
Consolidated | gam hybrid stock replace | done |  |  | CRX done, MRX not done
Consolidated | custom option-82 | in progress | Eric | 1.5.5
Consolidated | 3.3v sfp | done |  |  | sylvain…. Inductance
Consolidated | JSON syslog all 1970 | done
Consolidated | SFP power up | done
Sonifi | notch issue with 7.12 | done |  |  | problem master config not applied?
Samartaira | enable/disable port | done |  |  | also access parks
Zentro | cpu issue | done |  |  | split endpoints
ovation chicago | cpu issue | done |  |  | split endpoint multiple gam.
BAI connect | wrong endpoint supply NA with EU plug | done |  |  | shipped PS
shasta | OVA vcenter 8 | don't do it |  |  | replace by install script
flamingo | virtuoso server | done
parity | vistana random endpoint down | done
AWB | v1.2.0 | done
Parity | virtuoso ghost endpoints when replace, upgrade virtuoso | done
Parity | power glitch endpoint jam, more lightning issue | done
Pioner Connect | set MIMO or SISO via OMCI ?
IHG | virtuoso for Jose | done
Blue Shift | crash 24 suscribers trunk mode | done |  | 1.5.5 | 1.5.5 and trunk
COX | security report | in progress | Luc | 1.5.5
Blueshift | 24 subscribers in trunk, gam crash | in progress | JF | 1.5.5 | customer has a workaround. Eric did the fix. Not released yet 1.5.5
Blueshift | port up and down, wiring issue? Or power piggyback |  | Ronald |  | power issue with piggyback?
Home Grid | LCMP interop test Coax |  |  |  | p2mp 7_12, default domain and password
Home Grid | LCMP interop test MIMO |  |  |  | 7_8 SR3, default domain and password
Sheraton | document why gas tube | done |  |  | Artjom
IHG | no swagger intetration without virtuoso cloud
Choptank | electrical shock on endpoint
Getgrooven | Mikrotik SFP not working
Nexicom | video bypass bwp. Done g1000 but not g1002
View | access to license server
PROD/Shipping
| push 1.4 to production | done
| prod FS-GIGA | done
| buy printer licenses | done
| HP PC label printer backup | done
| PC Bobby | done
| PC Dinesh | done
| PC Kasia | done
| endpoint configured as master for prod, use old gam instead | done |  |  | rudy
| manufacturing load new GAM | done
| change ping/speedtest server | done
| shipping label MAC address and NA,UK,EU | done
| GAM-24-M new layout problem PHY 200ms reset | done
| Script eeprom | done
| g.hn master flash vitesse | don't do it |  |  | maxlinear current sw no support
| new label template put in agile | done
| 5 pc | done |  |  | rudy
| 5 scanners | done
| gam modifier pour programmer SFP XGS | done
| 4 packaging bartender | don't do it |  |  | decided not to do it
| push 1.5.4.r24791 to prod | done
| mfg server add column for test result | done
| gam-12-c with uart connector for rosemont | done
| push latest FW CPE |  |  |  | pas tres important. Gam will update cpe
test sfp -40
| association PIC SN and PAS SN |  | David |  | currently done in excel, wait for new architecture
| one CPE station dead | done | Rudy
| new station IMI | done | Rudy
| gateway tunnel IMI Mikrotik | in progress | JF
| document production procedure CPE | in progress | Max |  | draft done
| new load manufacturing with PHY workaround | done | Luc |  | Rudy to implement to prod
| XGSPON SFP, 50 good, no more cycle, only drop test. | done
| script fail because ghn telnet password | in progress | Rudy
HW
| 12v 3A (MR, CR) | done |  |  | Michael
| 48v sticker | done
| old design G1001-MR defect | done
certification UL MX CX and cpe
certification FCC all…....
| test new GAM indoor MIMO prod no TI | done
| spotcheck new GAM indoor COAX prod no TI | done
| BOM GAM-PWR-24 | done
| test new GAM outdoor Coax, noise improvement | done
| BRX-VDSL condo | done
| space for pre-scan | done
| AC power supply outdoor. | done |  |  | missing pcb and plug, need complete BOM
| Halo RJ-45 connector | done
| FPGA C+ and M+ | done
| DC-DC cable Phillips TV | done |  |  | issue keep power on endpoint
| add grommet for uplink gam outdoor. | done
| G1001-CR short latch | done
| G1001-C not as good as devolo or comtrend. Built-in splitter vs diplexer, remove 2nd port? | done |  |  | no proceed for now. eco and new face plate
| MR CR 350mA ECO or new 500mA | done |  |  | eco
| MR CR not enough power out 450mA or 500mA |  |  |  | prx126 3W or 10g copper
| G1002-M+ and C+ with RPF ??? |  |  |  | 2.5g phy?
| petit cable coax outdoor gam | done |  |  | scrap old ones?
| PRX onboard GAM or URX | done |  |  | go urx
| preprogram chip |  |  |  | cpe not important. Mips manuf. New PHY
| Sylvain tools | done
| fibre UPC/APC | done
| product code europe | done
| View new HW eeprom definition | done
| coax 90v | done
GAM-PSE
| G1001-C cost reduct remove second port |  |  |  | forecast many 10,000
| URX eval board | done |  |  | rc'd
| gam outdoor RPF coax hybrid noise | done |  |  | new layout not as good
| gam outdoor RPF mimo performance | done |  |  | also MR issue
| endpoint 48v boot issue | done |  |  | eco not implemented
| new punch block for 22 or 19 awg |  |  |  | ???
| GAM coax outdoor leakage port to port | done
| GAM prod with relay sfp power | done
| G1001-C gas tube and power brick | done
| cage SFP with heatsink |  | Sylvain |  | rec'd sample
| AC brick 4a and 1a high temp |  |  |  | problem with 3A also
| SFP XGS rev up for I temp | done
| new ASY for GPON PRX | done
12v 10A heat test
| 3A power supply dead | in progress | Sylvain
| G1002-M+ switch reset even with wire | done | Amin
| GAM-24-M new main with new piggyback. Port random reset | done | Sylvain |  | resistor for power and clock
| bracket gam outdoor plate sfp | don't do it |  |  | no go if heatsink ok
| gam4-c or cheap ONT-4-C indoor serval2, RLTK, URX |  |  |  | wallmount only or rackmount
ONT-2-C prx321
PSE w/PRX
static discharge
| mechanic after 6 months? | done |  |  | external consultant
FW
| endpoint VIEW | done
| virtuoso script vmware | done
| issue disable/enable port reset other port fake status MIMO | done
| issue disable/enable port reset other port real issue domain coax | done
| POE enable/disable reset endpoint | done
| verify BFT MAC limit coax | done
| verify BFT MAC limit MIMO | done
| try GAM with other flash | done
| Virtuoso VM not working with VMWARE. Ovf1.0 and network adapter | done
| NAT troughput eval board | done
| check GAM long uptime web gets slow | done
| 169.254 | done
| graph not working uplink/stacking coax | done |  |  | arp static
| new 1.4 for coax resync | done
| port 2 vlan not working when in allowed list | done
| TX power short loop | done
| second E7 shelf | done
| SMx | done
| traffic overview counters erroned 2.5G | done |  |  | eric
| 1.4 for lumen | done
improve debuglog
| PTP, not working as expected, maybe new vitesse version |  |  |  | on hold
| GAM announcement stop working, https only? |  | Eric |  | occurred when network is flooded. Loop
| graph min max chart.js |  |  |  | eric
graph in dBmV
web/CLI/JSON/SNMP mac table bft master
web/CLI/JSON/SNMP igmp snooping info from master
| GAM session manager |  | KK
| api memory usage | done | 1.5.5 |  | andrew, cli web done
interface vlan, dhcpclient ip only, option to ignore gw, dns
SR1 performance, speed up cdta, external core (prx)
| SR2 performance | don't do it |  |  | luc
| force 5 bands SISO for sym traffic. | done
| 32 endpoints per coax | don't do it |  |  | luc
| SISO ramp up 1-3-5 |  |  |  | SR3 ?
| JSON backup config | done |  |  | done 1.5, 1.4 ?
| flag in JSON for virtuoso or external config | don't do it
| L2 usable bandwidth | done |  |  | done 1.5 and 1.6
| new View GAM | done
| IGMP snooping bypass ACL. Cannot create rule to block queries |  |  |  | maybe not required
| starting with 1.6, remove .mfi | done |  |  | trunk, 1.5 and 1.4
| JSON syslog all 1970 | done
| GPY111 PHY issue | done
| DHCP snooping output always pcp 0 | done
| default config endpoint upgrade 1.5.5 | done |  | 1.5.5
| change order configured vs discovered endpoint | done | Eric | 1.5.5
| add subscriber at the top instead of bottom | done | Eric | 1.5.5
| disable snmp by default??? |  |  |  | security issue?
split allowed vlan 2 ports g1002
special character not working in URL e.g. password FTP
| merge andrew trunk to 1.5 | done | Luc | 1.5.5
cli not debug to find endpoint IP
| netconf/yang | don't do it
| gNMI | don't do it
| 1.6.0. Reload cold or upgrade reboot sfp | done |  |  | not seen with sdk18.2
| JSON command to set controller announcement | done |  | 1.5.5
| workaround factory reset ghn when configured in endpoint | done
| optimize discovery/config | done
| watchdog endpoint | done |  |  | 1.5.4...1002/2002 fpga 10
| LED SRV always red in daisy-chain | done |  | 1.5.5
| web noswap | done |  | 1.5.5
| option-82 add subscriber description | done | Eric | 1.5.5
| add ASY-2119-21 to trunk and 1.5 | done | Luc | 1.5.5
captive portal to associate MAC
| add default controller announcement virtuoso.positronaccess.com | done |  | 1.5.5
URX evaluation
OMCI | add OLT info in ONT discover |  | Luc
OMCI | publisher stop working | done | Martin | 2.0.1
OMCI | iphost stop working | done | Martin | 2.0.1
OMCI | image GPON PRX | in progress | Martin
OMCI | omci hostname
OMCI | finish limit 64 rules | done | Martin | 2.0.1
OMCI | add iphost dns to publish to GAM | done |  | 2.0.1
OMCI | workaround limit 64 rate limiter | in progress | Martin |  | double tag
OMCI | bandwidth profiles not precised ~40% less downstream, upstream looks better | in progress | Martin
OMCI | support 2 SFP per gam |  |  |  | ???
OMCI | ToD 50Hz sdk18 ? | don't do it
OMCI | support gam daisy-chain
OMCI | SISO MIMO
OMCI | endpoint or port aware
OMCI | only one port per endpoint, not possible to use second port |  |  |  | not even manually
OMCI | T-Bit support
OMCI | document upgrade by OLT |  | Luc
virtuoso
| Virtuoso firmware upgrade not working anymore | done
| session timout no login page | done
| session timeout configurable | done
| inactivity timer counts even if working on system | done
| doesn't support GAM-LBE | done
| daily backups of GAM config with library control | done
| REST northbound API , swagger | done
| session management, who is logged in | done
| software management, manage files from web instead of SCP | done
| GUI columns hide, select | done
| endpoint GAM-M many error | done
| bandwidth profile template | done
| install script for Rocky linux | done
google maps
discover topology daisy-chain with LLDP
| doesn't recognize v1.5.0 (maybe json api 1.2.1?) | done
| endpoint tab, add TX/RX speed | done
| subscriber double tag | done
| header VIRTUOSO | done
| login page banner | done
| manage timezone. Currently display UTC only. | done |  |  | system wide done, per session?
| be able to change sort of events new>old… currently old to new | don't do it |  |  | sort is working
| level 0-5-10-15 need 4 different session to connect to GAM | done
| radius | done
| TCA on bandwidth | done
hyperlink web proxy
| tunnel for cloud apps | in progress |  |  | Luc ssh tunnel POC done
| menuconfig.sh work with centOS nmcli instead of netplan | don't do it |  |  | chenaged with script instead
service auto-provisioning ex: default subscriber vlan
| manage virtuoso certificate | done |  |  | with linux procedure
manage gam certificate
snmp traps with endpoint subscriber descriptions
| swagger | done
| manage ntp all gam | done
| ghosts endpoints | done
| export template/import subscriber | done
| delete multiple endpoint and subscriber | done
| discover new gam set controller anouncement | done
send trap
| send email | done
picture library
service and port profile
| redesign production software | in progress | David
| uptime gam and endpoint. Detail and summary | done
add GAM MAC in column . Already exist in detail
MISC
| Ronald | done
| move daisy-chain to rack | done
| XGS-PON setup | done
| automation setup 2nd floor lab | done
| site survey check list | don't do it |  |  | artjom
GAM product selection guide
GAM FAQ document
CLI guide
| training videos | done |  |  | artjom
| pc and soft Luc Poulin | done
| GAM training PPT basic | done
| GAM training PPT advanced | don't do it |  |  | artjom
| Plugfest | done
| new GAM outdoor validate noise | done
| GPON-8 card | don't do it |  |  | never rc'd
| send G1002-C+, 2002-M+ to RGNets | don't do it
| waiting for GENERIC SFP OLT, ONU, 10GbaseT | done |  |  | received 10GbaseT
| Calix OLT transceiver fibermall x1 | done |  |  | not good
| 17 x PRX126 | done |  |  | recd 1 on nov21, eta mid-dec
| 6x champion one | done |  |  | rec'd 7 nov
| GPON OLT transceivers Calix PO | done |  |  | eta jan23
| Sonar demo | don't do it
| ETI demo | don't do it
| Devolo endpoint Coax MIMO | don't do it |  |  | coax done, mimo done but sr2 no vect
| aruba equipment. What is the goal | done
| graph hgf | done |  |  | rec'd reports
| GAM for ETI/sonar | done
| Fuse | don't do it
| Rgnets ? | don't do it
| Mikrotik switch | done
| add parts to price list | done |  |  | DC-DC cable, HPF, diplexer
renovation
| nouvelles chaises | done
| Pricing GAM-4-CX-AC | done
| static IP new build server | done
| Pricing GPON champion one sfp | done
| Pricing virtuoso license | in progress | Pierre
update datasheets
| resource FW | done
| resource QA | done
| release 1.4.0 |  |  |  | igmp fix, no need novus moved to 1.5.4
| release 1.5.x | done |  |  | disc,igmp,shut/noshut
| release 1.2.0 | done
| release 2.0.1 |  |  |  | wait for 1 bug fix Martin
| lab heat issue | done
bugzilla vs Jira
| Sal | don't do it
formule r&d meeting, sw hw se?
| move Sandra,Sean,Rudy | done
| approval | done
IT
| switch everybody to o365 | done |  |  | allan only 1 left
| laptop Paul | done |  |  | will use old HP
| new Qnap | done |  |  | allan
| Cisco smart login | done
| new firewall | done |  |  | cdms
| file server | done
security groups
| wifi PUBLIC network | done
remove local admin
| EST upgrade to v9 | done
| PC Art | done
| PC Ray | done
group policy marcos popup menu
finish secure wifi
secure FTP
Backup FTP
| unbrick RxG | done
| David Gomez | done
| Jira project | done
| service calls? | done |  |  | support email done
| split customerservice and support email | done |  |  | allan
| remove servicepositronacces | done |  |  | jason
| DHCP lab | done
new AC for lab spare
| 1012 in trunk mode | done
| sales@positronaccess.com | done
| 3 monitors 4K dell | done |  |  | 2 luc + 1 spare OCT26
| make Phillips TV working with multicast | done
| buy more monitors 4K …..6 | done |  |  | ongoing
| new employee David Brazeau | done
| SSD crutial DOA, waiting for replacement | done |  |  | dg
| cable d-port | done
| new PC Yanick Maximillian Laure Sara | done
| old PC etienne to new guy in prod | done
| ecrans 4K laure, Sean, new guy | done |  |  | ordered 2 sean + KK
| new server | done |  |  | eta 28 apr
| NAV for Sara | done
| Cleanup old email accounts and remove forward | done
| new laptop Mike | done
| PC ryzen 9 qty2 for buildserver | done
VM backup
| shutdown exchange, remove authoritive role | done
| positron-all group cleanup | done
| mfg-server01 increase RAM to 4GB | done
| compte Andrew | done
| upgrade old xd730 | done
upgrade old r410 for lab add RAM
move AP from my desk
| toll free service line | in progress | Rod |  | us/can ok, intl doesn't work, rod to check
| internet 250/250 or 1G | done | JF
| convert fax from telus to beanfield | done | Rod |  | done, not working, rod to check
| PBX send email not working |  | Rod |  | rod
| minisforum PC or beelink | done
| CorelDraw Luc P. | done
| laptop mamoune | done
| bugzilla not able to send email | done
add 2 AP in basement
| update certificate VPN tunnel ASA sigmapoint |  |  |  | waiting for me,CDMS Chris
| new subnet 192.168.104.x/24 for basement ASA port 3 | done
| ticketmaster DNS | done
| fibre 2e to basement | done
| PC dell to repair | done
| add Luc P. R&D group + report | don't do it
| hide mailbox andrew clara don | done
| 6 mini-PC ryzen 5 | done |  |  | ordered
| 2 ryzen 9 Amin, Rudy | done | Allan
split 192.168.96.0/21
| core switch lab + corporate | in progress | JF |  | lab installed, corporate ready
| replace PBX |  |  |  | Grandstream 6302 ~700$ +150/y support
| Keyboard/mouse | done | JF |  | ordered
| d-port-dvi hdmi-dvi cables | done | JF |  | ordered
| usb hub | done | JF |  | ordered
| VPN certificate invalid | in progress | Silvio
| new portal for GAM FW |  | Sandra, Juan