## TelephoneSol'nPI
Task Assigned To | Due Date | Completed | Hours | Status | Action Item | Comments
Kick Off Phase
Pradip / Donna | 2007-01-30 | 2007-01-30 | 1 | complete | Receive mandate to investigate VoIP PBX for the Power Division (supporting 20-50 employees) with full flexibility of international dialing | From Pradip Sheth
Donna | 2007-02-23 | 2007-02-23 | 6 | complete | RFP for Solution sent to Bell, Telus and Excel
Donna | 2007-03-08 | 2007-03-08 | 4 | complete | Review Proposals
Mr. Weiser | 2007-03-08 | 2007-03-08 | 1.5 | complete | Meet with Mr. Weiser to discuss solutions and budget | Wait until Claude Brission COO is onboard
Claude / Joey Trombino | 2007-04-14 | 2007-04-14 | 1 | complete | SLA agreement for IT Services to be outsourced from PTI to PI | see e-mail Claude
Mr. Weiser | 2007-04-14 | 2007-04-14 | 1 | complete | Received Authorization and budget for new Telephone solution / Internet and equip. | Approx. 50K budget
Marc Alexandres | 2007-07-24 | 9/31/2007 | 1.5 | complete | Update Visio diagram with PI infrastrucutre
Telus | 2007-07-24 | 2007-07-24 |  | complete | Visio Diagram required (Steve Paquet)
SUB TOTAL |  |  | 16
Initial Ordering and Preparation Phase
Donna | 2007-04-14 | 2007-04-14 | 2 | complete | Order TI line PRI | Install Dmarc Server Room 2nd floor (power)
Donna | 2007-04-14 | 2007-04-14 | 3 | complete | RFP/ Order TI Internet connection 1.5 Mbps | Tender to videotron, Telus and Bell. (Telus cheapest and can deliver quickly)
Donna / Alberto | 2007-04-14 | 2007-04-14 | 1 | complete | Floor plan for Server Cabinet authorization from Mr. Weiser
Sandra Cohen | 2007-04-14 | 2007-04-14 | 1.5 | complete | Get Total phone requirements from Sandra/ AD etc
Donna | 2007-07-14 | 2007-07-14 | 2 | complete | RFP / Order Server Cabinet | PPSS matched best pricing
Telus | 2007-07-23 | 2007-07-23 |  | complete | Install T1 Internet
ALL | 2007-07-24 | 2007-07-24 | 2 | complete | Kick off meeting with Telus Project Manager and Positron IT Staff
Donna | 2007-07-24 | 2007-07-24 | 6 | complete | Order/install cabling for analogues from 2nd Fl riser to Power D-mark
Luc Larochelle | 2007-07-25 | 2007-07-25 |  | complete | Send Donna Specs for USP
Telus | 2007-07-25 | 2007-07-25 |  | complete | Install T1 PRI (Voice) and Analgoue lines
Donna | 2007-07-27 | 2007-07-27 | 1.5 | complete | Order Cabling Catcom All Cubes and basement runs
Donna | 2007-07-27 | 2007-07-27 | 0.5 | complete | Send Line Fax Lines to Malanie
Mélanie Paquette | 2007-07-27 | 2007-07-27 |  | complete | Send Station review for Cisco Call Manager Express document to be filled out
Marc Alexandre / Alberto/ | 2007-08-01 | 2007-08-01 | 1 | complete | Follow up to have Eletcical outlets install for UPS and cabinet. | Marc Alex will follow up with Alberto.
Sandra Cohen | 2007-08-06 | 2007-08-06 |  | complete | Complete Cisco Call Manager Express document and return to Melanie | Form given to Sandra 24th, july
SUB TOTAL |  |  | 20.5
Phase II Network Setup and preparation
Marc Alexandre | 2007-07-24 | 2007-07-24 | 3 | complete | Test internet connection | J'ai testé la connection internet, ça fonctionne
Marc Alexandre / PPSS | 2007-07-30 | 2007-07-30 | 3 | complete | Install Server Cabinet | Waiting for Electrical outlet's for UPS, specs given to Alberto
CatCom | 2007-08-01 | 2007-08-01 |  | complete | Install / Recable Power Data jacks to D-mark area / including 4 cable runs from Basement to 2nd floor | Once Eletricity is in and Switch has been moved to cabinet
CatCom | 2007-08-01 | 2007-08-01 |  | complete | Cable Analogue lines to Lab and Fax
Marc Alexandre | 2007-08-01 | 2007-08-01 | 1 | complete | Confirm installation for Cabling with Cat Com once Electricity is done
Marc Alexandre | 2007-08-01 | 2007-10-08 | 3 | complete | Configure and deploy TZ170 | PI went live on VPN Tunnel to connect to Exchange and ManMan Oct. 4th 2007
Marc Alexandre | 2007-08-06 | 2007-08-06 | 3 | complete | Connect PI LAN Network to 4000 in Cabinet and test
Marc Alexandre | 2007-08-06 | 2007-08-06 | 4 | complete | Rack Servers and equipment (SRVAGIL05, 04, Switch Firewall and DC) | La switch 4000M est fonctionnelle lorsque branchée dans le jack 173 (testé)
SUB TOTAL |  |  | 17
Phase III Installation and configuration
Christian / Marc Alex. | 2007-08-31 | 2007-08-31 | 6 | complete | Deploy / Test Telephones to all Employees | Tony Basement not working
Telus | 2007-08-31 | 2007-08-31 |  | complete | Installation of Call Manager Express and configuration | Redundant power supply not compatible
Telus | 2007-08-31 | 2007-08-31 |  | complete | Installation of one or two phones to train Positron Technicians
Marc Alex | 2007-08-31 | 2007-08-31 | 1 | complete | Install UPS in rack
SUB TOTAL |  |  | 7
Phase VI Post Cut
Donna | 2007-09-04 | 2007-09-04 | 4 | complete | Train PI employees
Telus | 2007-09-04 | 2007-09-04 |  | complete | 1-888 number still being directed to 514-345-0254 and 514-789-2741 (no longer required). Must redirect to 514-345-2228 (then to SubMenu)
Telus | 2007-09-06 | 2007-09-06 |  | complete | Need to look into limitations in 1-800 incoming lines
Telus | 2007-09-06 | 2007-09-06 |  | complete | Some users prompted for user ID then password | Should be passwor only
Telus | 2007-09-06 | 2007-09-06 |  | complete | Directory not working (as discussed) | Corrected Sept. 6th
Telus | 2007-09-06 | 2007-09-06 |  | complete | Ext. 2442 ID seems to be unknown. Cannot activate
Telus | 2007-09-06 | 2007-09-06 |  | complete | Ext. 2461 and 2531 do not have a mailboxes associated.
Telus | 2007-09-06 | 2007-09-06 |  | complete | Yeh Hao Lu name not correct
Telus | 2007-09-06 | 2007-09-06 |  | complete | Ionela remove middle name
Christian / Telus | 2007-10-08 | 2007-10-28 | 0.5 | complete | Change Benoit Marleau's name to Consultant 1, Also Change Finance 1 to DAN…. And Finance 2 to Sandra Holder
Telus MAC / Donna | 2007-12-13 | 2007-12-17 | 0.5 | complete | Main menu changes default 0 action, Add Customer Service, Add local directory " For Marketing dial…, For Finance dial xxx… | Waiting on Claude to send me Menu Suggestions
Telus MAC / Donna | 2007-12-13 | 2007-12-17 | 0.5 | complete | When trying to access the "local Directory" on the phones, it does not show the list of employees, what can be done to add the names of the employees. Change to add employee names | Will wait for new Name Change Positron Access "4567 Claude Brission / Next line 514-345-2220"
Telus MAC / User Education | 2007-10-31 |  | 0.5 | Hold | Local speed dial programming on Conference Table phone Ext. 2031. User tried to change speed dial as indicated in hand out, unprogrammed phone
Telus MAC / Donna | 2007-12-13 | 2007-12-17 | 0.5 | complete | Password default for 2031 not working reset password 112031
Telus MAC / User Education | 2007-10-31 |  | 0.5 | Hold | Following up on our discussion a few days ago: can you find out if there is a way to get directly to a message on our new phones and avoid having to first listen to all the stuff about the phone number the call was made from, etc.? Regards, Ron
Telus MAC / User Education | 2007-10-31 |  | 0.5 | Hold | Find out how to move forward through messages
Telus MAC ref. #2 / Donna | 2007-12-13 | 2007-12-17 | 0.5 | complete | calling the 514-345-2220 number to leave a message on someone’s voice mail but all I got was “Nos bureau sont presentement ferme” in French only and that was it. The system would not allow me to reach anyone’s extension.
Telus Repairs ref. #1 / Donna | 2007-12-13 | 2007-12-17 | 0.5 | complete | Intermittant problem with Directory dialing. Sandra and Sal's line tested, sometimes call rings through, sometimes recorded name repeats without any other options.
Telus | 2007-09-06 | 2007-09-28 |  | complete | Send IP Communicator Softphone software
Telus | 2007-09-06 | 2007-09-06 |  | complete | Knowledge transfer on basic use of 7940 and 7960 phones
Telus | 2007-09-06 | 2007-09-06 |  | complete | Knowledge transfer on administration of Call Manager Express
Telus | 2007-09-06 | 2007-09-06 |  | complete | Knowledge transfer on administration of Call Manager Express
Telus | 2007-09-06 | 2007-09-06 |  | complete | Mr. Weiser`s cascade from 2231 to 2500 takes too much time (8 rings before it finally goes to VM)
Telus | 2007-09-06 | 2007-09-06 |  | complete | When an invalid extension is dialed the message should not be "I'm sorry, we are currently experiencing system problems and are unable to process your…."
Telus | 2007-09-23 | 2007-09-28 |  | complete | When we list the "missed calls" then want to dial the number missed, the system does not dial 9.. To get out. Can this be changed
Telus | 2007-09-06 | 2007-09-06 |  | complete | As three line Conf. Max seems to be an issue for the Exec. Assistant. Please supply me the cost of an upgrade solution. She would need max 6 conf. Lines at once | Now max 6 lines
Donna | 2008-01-15 |  | 5 | in progress | Documentation / Planning and tracking
Donna | 2008-01-15 |  | 2 |  | Transfer of knowledge for contacts / Documentation to PI Delegate
Donna | 2007-12-13 | 2007-12-17 | 4 | complete | Follow up no outstanding issues
Marc Alex / Telus | 2008-01-15 |  | 2 |  | Install and test IP Communicator Soft Phone
SUB TOTAL |  |  | 21.5
GRAND TOTAL |  |  | 65

## CM VM Limits
Description | Minutes | Seconds | Comments
Current Configuration
Default Mailbox Size | 15 | 900 | This is obviously the maximum number of seconds available for all the messages inside a mailbox
Default Caller Message Size | 7 | 420 | This is the value you asked me to change to 7 minutes. So actually, you cannot leave more than 2 messages, full-time
Maximum Recording Size | 5 | 300 | This is the available number of seconds to record your personal greeting
System Capacity | 840 | 50400 | This is the system capacity which inclused Auto Attendant recordings
840 - 10min for Auto Attendant recordings = 420 / 32 users = 25.62 - 5 min for personal recording = 20.62 min per user max mailbox. Problem;: no scalability to add new users. (more than 32)
Must verify if the Maximum Recording Size is included in the max mailbox size
Upgrade Costs approx $4K
Option 1
Default Mailbox Size | 20
Default Caller Message Size | 5 |  | Can leave Max 4 messages of 5 minutes (or 10 messages of 2 minutes) - less greeting time
Maximum Recording Size | 5
Option 2
Default Mailbox Size | 25
Default Caller Message Size | 5 |  | Can leave Max 5 messages of 5 minutes (or 12 messages of 2 minutes) less greeting time
Maximum Recording Size | 5
Description | Minutes | Seconds
Option Claude Authorized
Default Mailbox Size | 15
Default Caller Message Size | 5 |  | Can leave Max 5 messages of 5 minutes (or 12 messages of 2 minutes) less greeting time
Maximum Recording Size | 3
Exceptions |  |  | Alice Ext. 2233, Mr. Weiser, 2500, Cust. Support: 2431 (2nd line VM) Tech. Support: 2214 (2nd line VM)
Option
Default Mailbox Size | 35
Default Caller Message Size | 7
Maximum Recording Size | 5

## PostCut Issues
# | Current Post Cut Issue | Resolution (Telus response) | Est. hrs | Rate/hr | Cost | Auth. | J
1 | We need to change the action when dialing 0 at anytime, to call the 1-800 number, not "This is an invalid Choice, please try again" | This can be programmed remotely by changing the destination for all transfer points that the « 0 » connects to | 1.5 | 80 | 120 | Y | Reviewed with the team our issues with the Call Manager main menu when answering the main number 345-2220. One main issue is the need for dialing “1” and then the extension number, versus just dialing the extension number (which all start with a “2” – a menu item I assume we could eliminate). So, our preferred solution would be something like this (after the welcome message, dial 9 for English) : - for customer service, dial 3 now Whatever extension the Customer Service is going to now (it’s option 1 of the 1-800#) but we can’t see what the extension is - for technical support, dial 4 Whatever extension the Technical Support is going to now (it’s option 2 of the 1-800#) - for Marketing, dial 5 extension 2239 - for Accounting, dial 6 extension 2553 - for our coordinates, dial 7 (same voice message that exists – although if we are going to schedule another recording session, I would change this one to say the web-site first in the message) At any time, caller should be able to hit “*” or “0” to hear the menu again. If we can’t do the direct extension dialing, and we need to leave the “dial 1 then the extension”, then we need to make sure that the message of “dial 1 + the extension” is repeated instead of saying “that is an invalid entry” and leaving the caller guessing at what he did wrong (that seems to be the major issue), and then hanging up on the caller.
2 | When trying to access the "local Directory" on the phones, it does not show the list of employees, what can be done to add the names of the employees. | There is no directory because all sets names are « Positron ». So in the directory you would see « Positron » extension XXXX. We could add a directory, but each entry would be counted in double, meaning: all “Positron extension XXXX” would remain, plus the first, last names, and XXXX of the employee. | 1 | 80 | 80 | Y | Donna to find out about exceptions for Cust Support and Alice / Send another e-mail to MAC Nov 7th.
3 | "Local speed dial" option also is unavailable, is there anything which can be done to allow for speed dialing. | This also can be programmed remotely, but it has to be kept up to date by an administrator only. Requires xls spreadsheet | 2 | 80 | 160 | n
4 | I would like to know how many lines can the 1-800 line have incoming at one time? It is currently programmed to ring on two phones…what are the limitations. | There is 1 PRI with 23 b channels in and out coming. There could theoretically be 23 incoming calls on the 1-800 number at one time, on 1 phone. This could also be programmed remotely. We would need to know on which extension numbers and how many calls you would like to have the 1-800 number to ring. | 1.5 | 80 | 120 | n
5 | Is there any way to have internal name display different from external Name display? | Yes, but when dialing out, your customers would see what is programmed on the button. Voir point #2. Si la cliente choisi d’avoir le nom de l’employé à l’afficheur externe ou non. | 2 | 80 | 160 | n
6 | calling the 514-345-2220 number to leave a message on someone’s voice mail but all I got was “Nos bureau sont presentement ferme” in French only and that was it. The system would not allow me to reach anyone’s extension. | Ticket open with Telus, ref #2, must call MAC service this will be no charge. |  | 0 | 0
| TOTAL COST |  |  |  | 640

## Key Personnel
DATE:
Telephone Solution Positron Inc (PowerDivision)
TASK LIST
SPECIAL NOTES:
KEY PERSONNEL
COMPANY | NAME | TITLE | PHONE | CELL or PAGER | email | COMMENTS
Positron | Donna Koussaya | IT Networking Manager | 514-782-3111 Ext 4586 | 514-916-3687 | dkoussaya@positron.qc.ca
Positron | Marc Alexandre Belanger | Network Administrator | 514-345-2200 | 514-715-7813 | mabelanger@positron.qc.ca
Positron | Chritain Valet | Infrastructure Specialist | 514-782-3111 Ext 4205 |  | cvalet@positron.qc.ca
Positron | Claude Brission | COO, Positron Inc. |  |  | cbrission@positronpower.com
TELUS | Serger Guilbert | Senior Account Rep. National Accounts | (514) 788-8208 | (514) 577-0176 | serge.guilbert@telus.com
TELUS | Mélanie Paquette | Analyste de projet / Project Analyst | Tél.: 1.800.361.7181, poste 6974 |  | mailto:melanie.paquette@telus.com
TELUS | Luc Larochelle | Technicien Implantation II | DID: 514-798-4033 | Cell : 514-809-4835 | mailto:luc.larochelle@telus.com
TELUS | Eric Dumais | Technicien, Coordination de Projets Clients | 514.788.8782 |  | ERIC.DUMAIS@telus.com
TELUS | Mr Brian Leclerc (Replacing Eric) | Technicien, Coordination de Projets Clients | 514-788-8315
TELUS | Louis Cayer | Acount Manager | 514-788-8418 |  | louis.cayer1@telus.com
TELUS | Gaetano Carnevale | Expert Network Solutions Specialist | 514-788-8248 |  | gaetano.carnevale@telus.com